## Gantt Chart
CROWD METER 2.0 GANTT CHART
PROJECT TITLE |  | Gym Live Tracker
PROJECT MANAGER |  | Devan Desai
COMPANY NAME |  | Planet Fitness
DATE |  | 2023-01-25
STAGE NUMBER | TITLE | Dependency | TASK OWNER | START DATE | DUE DATE | DURATION (DAYS) | J A N U A R Y | [8 empty] | F E B R U A R Y | [27 empty] | M A R C H | [30 empty] | A P R I L
[7 empty] | WEEK 1 | [8 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
[7 empty] | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Project Initiation |  |  |  |  | 23 | Week 2 1: S T A G E 1
| Outreach |  | Everyone | 2023-01-23 | 2023-01-26 | 3 | bar: WEEK 1 23 to WEEK 1 25
| Project Description | Outreach | Devan | 2023-01-26 | 2023-01-29 | 3 | bar: WEEK 1 26 to WEEK 1 28
| Elevator Pitch | Project Description | Huzaifah | 2023-02-05 | 2023-02-08 | 3 | bar: Week 2 5 to Week 2 7
| Who We Are | Outreach | Everyone | 2023-01-29 | 2023-02-09 | 10 | bar: WEEK 1 29 to Week 3 8
| Initial Research | Outreach | Electra | 2023-01-29 | 2023-02-08 | 9 | bar: WEEK 1 29 to Week 3 8
| Stakeholders | Who We Are | Deyondre | 2023-02-06 | 2023-02-14 | 8 | bar: Week 2 6 to Week 3 13
| Target Audience | Who We Are | Electra | 2023-02-03 | 2023-02-13 | 10 | bar: Week 2 3 to Week 3 12
| Scope | Initial Research | Huzaifah | 2023-02-03 | 2023-02-13 | 10 | bar: Week 2 3 to Week 3 12
| Preliminary Plan | Initial Research | Devan | 2023-02-11 | 2023-02-15 | 4 | bar: Week 3 11 to Week 3 14
| Short/Long Term Plan | Preliminary Plan | Devan | 2023-02-12 | 2023-02-15 | 3 | bar: Week 3 12 to Week 3 14
2 | Initial Research | The Pitch |  |  |  | 14 | Week 4 17: S T A G E 2
| Stage 1 Feedback Edits | Project Initiation | Everyone | 2023-02-15 | 2023-02-21 | 6 | bar: Week 4 15 to Week 4 20
| Primary Market Research Plan | Stage 1 Feedback Edits | Everyone | 2023-02-21 | 2023-02-28 | 7 | bar: Week 4 21 to Week 5 27
| Magic Quadrant & Conclusion | Primary Market Research Plan | Devan | 2023-02-21 | 2023-02-28 | 7 | bar: Week 4 21 to Week 5 27
| SWOT Analysis & Conclusion | Primary Market Research Plan | Electra | 2023-02-21 | 2023-02-28 | 7 | bar: Week 4 21 to Week 5 27
| Project Financials | Magic Quadrant & Conclusion | Everyone | 2023-02-21 | 2023-02-28 | 7 | bar: Week 4 21 to Week 5 27
| Summary Impact | SWOT Analysis & Conclusion | Huzaifah | 2023-02-27 | 2023-03-01 | 4 | bar: Week 5 27 to Week 5 28
| Update Project Plan | Summary Impact | Devan | 2023-02-27 | 2023-03-01 | 4 | bar: Week 5 27 to Week 5 28
3 | Detailed Research | The Supporting Details |  |  |  | 28 | Week 7 13: S T A G E 3
| Stage 2 Feedback Edits | Initial Research | Everyone | 2023-03-01 | 2023-03-05 | 4 | bar: Week 6 1 to Week 6 4
| Project ethics, security, and privacy | Primary & Secondary market research | Huzaifah | 2023-03-02 | 2023-03-07 | 5 | bar: Week 6 2 to Week 6 6
| Primary & Secondary market research | Stage 2 Feedback Edits | Electra | 2023-03-01 | 2023-03-23 | 22 | bar: Week 6 1 to Week 9 22
| Flow Diagram | Primary & Secondary market research | Electra | 2023-03-05 | 2023-03-08 | 3 | bar: Week 6 5 to Week 6 7
| Draft UI/UX design | Flow Diagram | Deyondre | 2023-03-02 | 2023-03-11 | 9 | bar: Week 6 2 to Week 7 10
| Low fidelity prototype | Primary & Secondary market research | Devan | 2023-03-11 | 2023-03-16 | 5 | bar: Week 7 11 to Week 8 15
| High fidelity prototype | Low fidelity prototype | Deyondre | 2023-03-16 | 2023-03-22 | 6 | bar: Week 8 16 to Week 8 21
| Summary Impact | Primary & Secondary market research | Huzaifah | 2023-03-22 | 2023-03-28 | 6 | bar: Week 9 22 to Week 10 31
| Update Project Plan | Summary Impact | Devan | 2023-03-26 | 2023-03-29 | 3 | bar: Week 9 26 to Week 10 4
4 | Project Implementation | Supporting Details and Solution Design |  |  |  | 14 | Week 10 30: S T A G E 4
| Stage 3 Feedback Edits | Detailed Research | Everyone | 2023-04-05 | 2023-04-08 | 3 | bar: Week 11 5 to Week 11 8
| Final High fidelity prototype | High fidelity prototype | Deyondre | 2023-04-07 | 2023-04-20 | 13 | bar: Week 11 7 to Week 12 20
| Lessons Learned | Meeting 35 | Everyone | 2023-04-14 | 2023-04-23 | 9 | bar: Week 12 14 to Week 12 23
| Detailed Appendeces | Project Implementation | Everyone | 2023-04-17 | 2023-04-25 | 8 | bar: Week 12 17 to Week 12 26
| Project Peer Management |  |  |  |  | 0
| Initial Peer Review |  | Everyone | 2023-03-01 | 2023-03-01 | 0 | bar: Week 6 1
| Final Peer Review |  | Everyone | 2023-04-12 | 2023-04-26 | 14
Meetings
| Meeting 1 |  | Everyone | 2023-01-27 | 2023-01-27 | 0 | bar: WEEK 1 27
| Meeting 2 |  | Everyone | 2023-01-29 | 2023-01-29 | 0 | bar: WEEK 1 29
| Meeting 3 |  | Everyone | 2023-01-31 | 2023-01-31 | 0 | bar: WEEK 1 31
| Meeting 4 |  | Everyone | 2023-02-05 | 2023-02-05 | 0 | bar: Week 2 5
| Meeting 5 |  | Everyone | 2023-02-06 | 2023-02-06 | 0 | bar: Week 2 6
| Meeting 6 |  | Everyone | 2023-02-10 | 2023-02-10 | 0 | bar: Week 3 10
| Meeting 7 |  | Everyone | 2023-02-11 | 2023-02-11 | 0 | bar: Week 3 11
| Meeting 8 |  | Everyone | 2023-02-12 | 2023-02-12 | 0 | bar: Week 3 12
| Meeting 9 |  | Everyone | 2023-02-14 | 2023-02-14 | 0 | bar: Week 3 14
| Meeting 10 |  | Everyone | 2023-02-20 | 2023-02-20 | 0 | bar: Week 4 20
| Meeting 11 |  | Everyone | 2023-02-21 | 2023-02-21 | 0 | bar: Week 4 21
| Meeting 12 |  | Everyone | 2023-02-26 | 2023-02-26 | 0 | bar: Week 5 26
| Meeting 13 |  | Everyone | 2023-02-27 | 2023-02-27 | 0 | bar: Week 5 27
| Meeting 14 |  | Everyone | 2023-02-28 | 2023-02-28 | -2 | bar: Week 5 28
| Meeting 15 |  | Everyone | 2023-03-02 | 2023-03-02 | 0 | bar: Week 6 2
| Meeting 16 |  | Everyone | 2023-03-06 | 2023-03-06 | 0 | bar: Week 6 6
| Meeting 17 |  | Everyone | 2023-03-07 | 2023-03-07 | 0 | bar: Week 6 7
| Meeting 18 |  | Everyone | 2023-03-08 | 2023-03-08 | 0 | bar: Week 7 8
| Meeting 19 |  | Everyone | 2023-03-13 | 2023-03-13 | 0 | bar: Week 7 13
| Meeting 20 |  | Everyone | 2023-03-14 | 2023-03-14 | 0 | bar: Week 7 14
| Meeting 21 |  | Everyone | 2023-03-17 | 2023-03-17 | 0 | bar: Week 8 17
| Meeting 22 |  | Everyone | 2023-03-18 | 2023-03-18 | 0 | bar: Week 8 18
| Meeting 23 |  | Everyone | 2023-03-19 | 2023-03-19 | 0 | bar: Week 8 19
| Meeting 24 |  | Everyone | 2023-03-22 | 2023-03-22 | 0 | bar: Week 9 22
| Meeting 25 |  | Everyone | 2023-03-23 | 2023-03-23 | 0 | bar: Week 9 23
| Meeting 26 |  | Everyone | 2023-03-24 | 2023-03-24 | 0 | bar: Week 9 24
| Meeting 27 |  | Everyone | 2023-03-27 | 2023-03-27 | 0 | bar: Week 9 27
| Meeting 28 |  | Everyone | 2023-03-28 | 2023-03-28 | 0 | bar: Week 9 28
| Meeting 29 |  | Everyone | 2023-03-29 | 2023-03-29 | 0 | bar: Week 10 29
| Meeting 30 |  | Everyone | 2023-04-01 | 2023-04-01 | 0 | bar: Week 10 1
| Meeting 31 |  | Everyone | 2023-04-02 | 2023-04-02 | 0 | bar: Week 10 2
| Meeting 32 |  | Everyone | 2023-04-03 | 2023-04-03 | 0 | bar: Week 10 3
| Meeting 33 |  | Everyone | 2023-04-06 | 2023-04-06 | 0 | bar: Week 11 6
| Meeting 34 |  | Everyone | 2023-04-07 | 2023-04-07 | 0 | bar: Week 11 7
| Meeting 35 |  | Everyone | 2023-04-10 | 2023-04-10 | 0 | bar: Week 11 10
| Meeting 36 |  | Everyone | 2023-04-13 | 2023-04-13 | 0 | bar: Week 12 13
| Meeting 37 |  | Everyone | 2023-04-15 | 2023-04-15 | 0 | bar: Week 12 15
| Meeting 38 |  | Everyone | 2023-04-17 | 2023-04-17 | 0 | bar: Week 12 17
| Meeting 39 |  | Everyone | 2023-04-19 | 2023-04-19 | 0 | bar: Week 12 19
| Meeting 40 |  | Everyone | 2023-04-22 | 2023-04-22 | 0 | bar: Week 12 22
| Meeting 41 |  | Everyone | 2023-04-24 | 2023-04-24 | 0 | bar: Week 12 24
Presentations
| The Pitch |  | Everyone | 2023-02-15 | 2023-02-15 | 0 | bar: Week 4 15
| The Supporting Details |  | Everyone | 2023-03-01 | 2023-03-01 | 0 | bar: Week 6 1
| Supporting Details and Solution Design |  | Everyone | 2023-03-29 | 2023-03-29 | 0 | bar: Week 10 29
| Final Presentation |  | Everyone | 2023-04-26 | 2023-04-26 | 0 | bar: Week 12 26